## About (hidden)
About this Workbook
Enter milestone and task information in the Chart Data worksheet. To chart milestones along the timeline, enter 0 in the No. column, then, update the label position to be "below" to avoid overlapping labels. The position column in the milestone table, charts milestones within the task chart either on the same row or in stacked rows. To chart them on the same row, enter the same number in this column for each milestone. To chart them on different rows, enter different numbers. Sample data charts all milestones along the row position of 2.
Guide for screen readers
There are 4 worksheets in this workbook. Chart Data Gantt Chart Dynamic Chart Data (Hidden) About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. Hidden text will not print. To remove these instructions from any worksheet, simply delete column A.
Dynamic Chart Data (Hidden)
Do not delete or modify content in the Hidden worksheet. Doing so could compromise the integrity of the Gantt Charting. Data may appear blank, dates may appear to be incorrect, do not fill in, edit, delete or otherwise modify the data or you risk overwriting formulas and breaking the chart graphing capability. The DynamicMilestone table allows for 15 milestones to be charted. To chart more than 15, simply expand the table to accommodate your number. Remember, only add the actual milestone data in the Chart Data worksheet.
Tips
By default, milestones are charted on row 1 of the Gantt Chart using the Position column in the Chart Data worksheet, starting in cell C5. To chart milestones on different rows, simply change the number.
The default setting is to highlight today's date in the Gantt Chart. To no longer highlight Today's date, simply select "no" in the Chart Data worksheet in cell D2.
The Gantt Chart date timeline is charted with a gap of 5 dates between them. To change this, select the timeline in the Gantt Chart worksheet and select Format Axis. Change the Major unit from 5 to 1 or 10, for example.
This is the last instruction in this worksheet.

## minter
Create a Date Tracking Gantt Chart in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. |  |  |  |  | ProjectTimeline Tracking
Select option Yes in cell D2 if you want to highlight today's date in the Gantt Chart worksheet. Select option No in cell D2 if you do not want to highlight today's date in the Gantt Chart worksheet. In Cell D2, select ALT+Arrow Down for options. | Track today's date? |  | Yes
Milestones header for the milestone table is in cell B3. Tasks header for the tasks table is in cell G3. |  | Tasks Timeline |  |  |  |  | Tasks Details |  |  |  | TASK
Information about the columns in the milestone table are in this row from cells B4 through E4. Information about the columns in the tasks table are in this row from cells G4 through J4. |  | This column should be ordered sequentially. | Enter the start date for each task below. For best results sort this column in ascending order. | Enter the end date for each task or activity below, in this column. | Enter tasks and/or activities in this column. | Auto calculated column used for charting the duration of each task. Do not delete or modify.
Milestone table headers are in cells B5 through E5. Tasks table headers are in cells G5 throughJK5. Milestone sample data is in cells B6 through E17. Tasks sample data is in cells G6 through J17. The next instruction is in cell A21. |  | No. | Start Date | End Date | Activity | Duration in days | Stages | Activities Description | Priority | Status | Step 2 | Activity Description | Priority | Status
|  | 1 | 2020-02-04 | 2020-02-10 | Activity 1 | 7 | (2) Designing the Experiment | (1) Sourcing a dataset | high | Done | Designing the Experiment | (1) Sourcing a dataset | high | Working
|  | 2 | 2020-02-04 | 2020-02-10 | Activity 2 | 7 |  | (2) Finding source code for SARIMA model | high | Done |  | (2) Finding source code for SARIMA model | high | Working
|  | 3 | 2020-02-04 | 2020-02-10 | Activity 3 | 7 |  | (3) Finding source code for LSTM model | high | Done |  | (2) Finding source code for BP model | high | Working
|  | 4 | 2020-02-11 | 2020-03-04 | Activity 4 | 23 |  | (4) Finding source code for BP model | high | Done |  | (2) Finding source code for LSTM model | high | Working
|  | 5 | 2020-02-11 | 2020-04-03 | Activity 5 | 53 |  | (5) Finding source code for Neaural ODEs model | high | Done |  | (2) Finding source code for Neaural ODEs model | high | Working
|  | 6 | 2020-02-18 | 2020-02-24 | Activity 6 | 7 |  | (6) Running test experiments for SARIMA | med | Done |  | (3) Running the experiment | high | Working
|  | 7 | 2020-02-18 | 2020-02-24 | Activity 7 | 7 |  | (7) Running test experiments for LSTM | med | Done
|  | 8 | 2020-02-20 | 2020-03-17 | Activity 8 | 27 |  | (8) Learning more about the inner workings of the Neural Ode code | high | Done
|  | 9 | 2020-03-18 | 2020-04-02 | Activity 9 | 16 |  | (9) Running test experiment for Neural Odes | med | Done
|  | 10 | 2020-04-03 | 2020-04-11 | Activity 10 | 9 |  | (10) Running test experiemnts for BP | med | Done
|  |  | 2020-03-17 | 2020-04-13 | Activity 11 | 28 | (3) The experiment process | (11) Running the actual experiement on the models | high | Done
|  |  | 2020-04-14 | 2020-04-27 | Activity 12 | 14 |  | (12)Rerunning the experiments on outtstanding datasets | high | Done
|  |  | 2020-04-28 | 2020-05-15 | Activity 13 | 18 |  | (13) Paper Write up and presentation | high | Done
To add more Milestones, add a new row above this one. Note, the default number of milestones to chart is 15. Adding new milestones requires a change in the hidden worksheet. See the About worksheet cell A9 for more information. The next instruction is in cell A26.
A note is in cell G26. This is the last instruction in this worksheet. |  | To add more Tasks, add a new row above this one.
Formulas:
End Date = Tasks[[#This Row],[Start Date]]+6